## Slide 1
GROUP 4 · PROJECT MANAGEMENT
CareerCompass AI
An AI-Powered Placement Preparation Platform
Final Project Deck | Business Process & Project Management
TEAM
Luv Singhal
P2512037
Umang Parakh
P2514072
Prateek Raj Dubey
P2513050
Tanisha Bhola
P2514067
Harshul Gupta
P2514030
Priyanka
P2512052
Tarana Bansal
P2513070

## Slide 2
The Problem
MBA students lack a single, AI-assisted platform to prepare for placements — leaving preparation fragmented, inconsistent, and invisible to the Placement Cell.
Fragmented Workflow
No single source of truth linking resume, JD, and application status
Inconsistent Prep Quality
Readiness depends on individual initiative, not a structured process
No Institutional Visibility
Placement Cell has no real-time view of batch-wide readiness
Manual, Non-Scalable Tracking
Excel-based tracking causes data lag and duplicated effort
PROJECT INTRODUCTION
CareerCompass AI
An AI-Powered Placement Preparation Platform for MBA Students
CareerCompass AI consolidates 13 fragmented placement-preparation activities — resume building, JD interpretation, ATS scoring, interview prep, and progress tracking — into one AI-native platform. It replaces a workflow currently spread across ChatGPT, LinkedIn, Glassdoor, Excel, and email/calendar tools, converting placement preparation from an unstructured activity into a measurable, institutionally governed process. Delivery is governed under a hybrid Agile-Predictive model, aligned to PMBOK 7 and the PMI Agile Practice Guide.
PROJECT SNAPSHOT
8 Months
Duration (34 wks incl. buffer)
₹58.40L
Budget at Completion
13
Integrated Modules
7
Cross-Functional Team
Expected outcome: ~60–70% reduction in per-student preparation time, replacing 7 fragmented tools with 1 platform.

## Slide 3
PROJECT CHARTER
CareerCompass AI
AI-Powered Placement Preparation Platform for MBA Students
8 Months
Timeline: 34 weeks incl. schedule buffer
₹58.40L
Total Budget at Completion (BAC)
7
Cross-functional delivery team members
GOVERNANCE MODEL
Hybrid Predictive-Charter / Agile-Execution: governed under PMBOK 7 + PMI Agile Practice Guide
BUSINESS CASE (OBJECTIVES)
Fragmented, tool-hopping placement prep leaves student readiness inconsistent and the Placement Cell without real-time visibility. CareerCompass AI consolidates 13 workflows into one AI-native platform — targeting a 60–70% cut in per-student preparation time and a reusable institutional data asset for future placement-training decisions.
SMART OBJECTIVES : BINDING CHARTER COMMITMENTS
O1
All 13 Modules Live
Production deployment, Month 8
O2
≥80% Match Precision
Resume–JD engine, validated at UAT
O3
≥70% Adoption
Active cohort within 4 weeks of launch
O4
CPI ≥ 0.95
Cost performance index at closure
O5
≥99% Uptime
Peak season; AI latency <5 sec (p95)
O6
Zero Critical Findings
Data-privacy audit, pre-launch
APPROVAL AUTHORITY (STAKEHOLDERS)
Project Sponsor
Placement Cell
Final approval on scope, budget, and Go-Live decision
Steering Committee
Placement Cell + Institute IT
Monthly governance; approves changes above ₹1,00,000 impact
Project Manager
Assigned PM
Day-to-day scope, schedule, and resource decisions within charter bounds
Confidential - Internal Governance Document | This Charter formally authorizes the Project Manager to apply organizational resources, per PMBOK guidance.

## Slide 4
PROJECT SCOPE
Scope: In, Out & Under Control
Release 1.0 delivers 13 modules across 4 clusters — with a firm, change-controlled boundary.
13
Integrated modules, v1.0
AI Intelligence
Resume analyzer, JD matching, ATS score
Preparation
Company research, interview prep, roadmap
Student Management
Tracker, scheduler, prep dashboard
Placement Cell
Learning recs, analytics dashboard
OUT OF SCOPE → FUTURE
• Native mobile apps → Phase 2
• Recruiter portal → post-legal review
• Live human interviews → AI-simulated only
• ERP/SIS integration → automated sync later
• Multi-language → English only in v1.0
Scope discipline: v1.0 = committed delivery. Future scope = roadmap, not hidden scope.
CHANGE CONTROL
Any Future/Out-of-Scope pull-in becomes a formal Change Request.
1
Requested
2
Formal CR filed
3
Impact assessed (cost/schedule/AI path)
4
Steering Committee approves
5
Implemented
8 Months · ₹58.40L · Hybrid governance

## Slide 5
WORK BREAKDOWN STRUCTURE
WBS: 10 Phases, 19 Activities, 31 Weeks
Scope broken into manageable deliverables; every work package maps to one schedule Activity ID (A–S).
Full WBS-to-schedule activity mapping available in appendix.

## Slide 6
SCHEDULE ANALYSIS
Critical Path, Confidence & Reality Check
19 activities, finish-to-start — one shared bottleneck drives the whole schedule risk.
Activity Network & Critical Path
31 weeks, 14/19 activities zero-float — two paths converge at System Integration (O).

## Slide 7
PROJECT SCHEDULE · MICROSOFT PROJECT EXPORT
CareerCompass AI — Master Project Schedule
19 tasks · 12 Aug 2026 – 03 Jun 2027 · ~31 weeks · Critical path shown in red
ID
Task Name
Dur.
Start
Finish
Pred.
Aug'26
Sep'26
Oct'26
Nov'26
Dec'26
Jan'27
Feb'27
Mar'27
Apr'27
May'27
Jun'27
1
Charter & Kick Off
7 days?
12/08/26
20/08/26
7d
2
Stakeholder Analysis & Planning
8.75 days
21/08/26
02/09/26
1
8.75d
3
Requirement Gathering
21 days
02/09/26
01/10/26
2
21d
4
Architecture & Tech Stack Finalization
14 days
01/10/26
21/10/26
3
14d
5
UX Wireframing
14 days
01/10/26
21/10/26
3
14d
6
Hi-Fi UI Design
14 days
21/10/26
10/11/26
5
14d
7
Backend Core Setup
21 days
21/10/26
19/11/26
4
21d
8
Frontend Core Setup
21 days
10/11/26
09/12/26
4;6
21d
9
AI: Resume Analyzer
28 days
19/11/26
29/12/26
7
28d
10
AI: Matching Score
21 days
29/12/26
27/01/27
9
21d
11
AI: Interview Question Gen
35 days
29/12/26
16/02/27
9
35d
12
Company Dashboard
21 days
09/12/26
07/01/27
7;8
21d
13
Tracker/ Prep Dashboard
21 days
09/12/26
07/01/27
7;8
21d
14
Analytics Dashboard
14 days
27/01/27
16/02/27
10;12
14d
15
System Integration
14 days
16/02/27
08/03/27
11;13;14
14d
16
QA (Functional + AI Accuracy)
28 days
08/03/27
15/04/27
15
28d
17
UAT (Students + Placement Cell)
14 days
15/04/27
05/05/27
16
14d
18
Deployment & Go-Live
14 days
05/05/27
25/05/27
17
14d
19
Closure & Handover
7 days
25/05/27
03/06/27
18
7d
Critical task
Non-critical (float)

## Slide 8
Resource Planning
19
Activities
7
Resource roles
1.8
Max activity FTE
1.0
Single-role capacity
ACTIVITY
PM
BA
UI/UX
Frontend
Backend
AI/ML
QA
TOTAL FTE
Charter & Kickoff
1
0.5
1.5
Stakeholder & Planning
0.5
1
1.5
Requirement Gathering
0.5
1
0.2
1.7
Architecture & Tech Stack
0.3
0.2
0.8
1.3
UX Wireframing
0.2
1
1.2
Hi-Fi UI Design
0.2
0.8
0.8
1.8
Backend Core Setup
0.1
0.3
1
1.4
Frontend Core Setup
0.1
0.9
0.4
1.4
AI: Resume Analyzer / JD Simplifier
0.1
0.4
0.3
1
1.8
AI: Matching Score / ATS Checker
0.1
0.5
0.2
1
1.8
AI: Interview Q-Gen / Mock Module
0.1
0.5
1
1.6
Company Dashboard / Roadmap
0.1
0.9
0.2
1.2
Tracker / Scheduler / Prep Dashboard
0.1
0.9
0.2
1.2
Analytics Dashboard / Learning Reco
0.1
0.8
0.3
1.2
System Integration
0.2
0.5
0.4
0.4
1.5
QA (Functional + AI Accuracy)
0.2
0.2
0.4
1
1.8
UAT (Students + Placement Cell)
0.3
0.4
0.8
1.5
Deployment & Go-Live
0.2
0.2
0.3
0.7
1.4
Closure & Handover
0.5
0.3
0.2
1
Planning insight | AI, UI and QA-heavy activities create the key capacity peaks that resource levelling must smooth.
ACTIVITY LOAD
Total FTE | highest first
Hi-Fi UI Design
AI: Resume Analyzer
AI: Matching Score
QA (Functional + AI
Requirement Gathering
AI: Interview Q-Gen
Charter & Kickoff
Stakeholder & Planning
System Integration
UAT (Students + Placem

## Slide 9
Resource Levelling
3.3 FTE
Peak demand
Before
1.0 FTE
Role capacity
Per resource
W16
Peak week
Highest load
W31
CPM finish
Protected
BEFORE — RESOURCE DEMAND
LEVELLING ACTIONS
01
Use float
Shift M within its available float W14–16 → W18–20
02
Redistribute
Split Frontend / Backend workload across overlapping activities
03
Sequence AI
Control J/K overlap + QA support for AI test-harness work
04
Protect path
Do not move critical-path completion beyond Week 31
AFTER
Demand peaks are smoothed without changing W31 completion.
PM DECISION | Level first using float + workload redistribution; crash only if management values earlier completion.
0
1
2
3
4
W1
W8
W16
W24
W31
3.3 FTE peak

## Slide 10
Project Crashing
Selective compression of critical-path activities to accelerate completion — without compromising the Week 34 deadline
31 → 29
Weeks
2 weeks faster
₹1.05L
Incremental cost
Crash investment
₹52.5K
Cost / week saved
Average crash cost
5 WEEKS
Remaining buffer
Against Week 34
1 | WHERE DID WE CRASH?
O
System Integration
2 → 1 wk
1 wk saved
₹50K
Common post-merge critical path
P
QA (Functional + AI Accuracy)
4 → 3 wk
1 wk saved
₹55K
Common post-merge critical path
SELECTION LOGIC
Crash activities that sit on the common critical path — otherwise the time saved may not reduce project duration.
2 | CRASHING PATH
NORMAL
31 WEEKS
Baseline CPM
→
O
−1 WK
₹50K
→
P
−1 WK
₹55K
→
RESULT
29 WK
−2 WK
COST IMPACT
O
₹50K
+
₹55K
=
₹1.05L
3 | SCHEDULE IMPACT
W29 Crashed
W31 Normal
W34 Deadline
5-week buffer to deadline
PM TAKEAWAY | We crash O and P because each saves 1 week on the common critical path; ₹1.05L buys 2 weeks of acceleration.

## Slide 11
The governance rhythm that keeps the AI-heavy critical path under control
TOP RISKS (P × I)
R1
16 High
AI Hallucination in generated interview content
Prompt guardrails + human-reviewed fallback bank
R8
12 Medium
AI-module schedule risk (dual critical path)
de-scope AI polish features if needed
R6
10 Medium
Data privacy breach (student PII)
Encryption, RBAC, pre-launch security audit
QUALITY GATES
Zero Sev-1 defects open at Go-Live
≥80% AI matching-engine precision
< 5 sec AI response latency (p95)
≥4.0/5 User satisfaction (CSAT)
QA PRACTICE
Shift-left QA from Sprint 3, peer code review on every PR, and a Definition-of-Done gate before any story ships.
COMMUNICATION CADENCE
Daily
Standup
Dev Team
Bi-weekly
Sprint Review & Retro
Team + Placement Cell
Bi-weekly
Risk & Issue Review
PM + Risk Owners
Monthly
Steering Committee Report
Sponsor + College Admin
Governance rhythm | weekly risk reviews, shift-left QA and monthly steering keep R1/R8 contained without slowing sprints.
RISK, QUALITY & COMMUNICATION

## Slide 12
MONITORING & CLOSURE
Budget Performance, Course Correction & Closure
Week-20 CPI dip triggered a targeted correction; project closes with zero Sev-1 defects.
CPI
0.94
SPI
0.95
CV
−₹2.20L
EAC
₹62.13L
BAC ₹58.40L · Target CPI ≥0.95 · Snapshot: Week 20 of 34
Course Correction
• Crash O→P: 31→29 wks for ₹1.05L
• Level resources: smoothed 3.3 FTE peak
• Queue AI/ML backup for J/K repeat risk
Closure Checklist
• Functional + UAT sign-off, zero Sev-1
• Handover, docs & privacy audit filed
• 3-week hypercare, then formal sign-off
Lessons Learned
• Single-skill dependency = top risk
• PERT variance flagged it before it hit
• Crash only the common critical path
• Hybrid governance kept scope disciplined